## Slide 1
YANA
77-79 Cecil Avenue & 25 Hume Avenue, Castle Hill · Dharug Country
HDA expression of interest · concept scheme · SSD with concurrent rezoning
Indicative only — not for determination. Draft for owner review, loop 3, 5 October 2026.
Notes: Cover. Indicative only — not for determination.

## Slide 2: 243 homes, 623 m from Castle Hill Metro, with 3% affordable housing in perpetuity
PROPOSITION
243
homes
133.9 m
height incl. 6 m tolerance
623 m
walk to Metro
3%
affordable, in perpetuity
FACT
2,048 m² corner site at Cecil and Hume Avenues, zoned R4 High Density Residential.
Source: Pack p2, p14
DESIGN PROPOSITION
A single tower, 133.9 m including a 6 m design tolerance: 38 residential storeys plus rooftop plant on a podium. 28,865 m² GFA (14.09:1).
Source: Pack p24; storey count with planner
MATTER FOR FUTURE
ASSESSMENT
Final height, floor space, affordable dwelling count and impacts are put forward for testing through SEARs, design review and exhibition.
Notes: Indicative only — not for determination.

## Slide 3: A consolidated corner site within a 10-minute walk of Metro, buses and centre services
SITE AND ACCESS
FACT
About 623 m walk to Castle Hill Metro: Chatswood about 20 minutes, Sydney CBD about 35 minutes.
Source: Pack p2, p7, p8
FACT
Bus routes 600, 603 and 610X stop on Old Northern Road, about 7 minutes' walk.
Source: Pack p8
FACT
Castle Towers, Castle Mall, the library, schools and the police station are within walking distance.
Source: Pack p12
FACT
Three lots, Lots 1-3 DP 713156 (25 Hume Ave, 79 Cecil Ave, 77 Cecil Ave), in consolidated ownership. No further amalgamation needed.
Source: Pack p3; owner 5 Oct 2026; title evidence to follow
DRAWING PLACEHOLDER
Brief B-2: Measured walking-route plan to Castle Hill Metro
To: Urbis / Arcadia
Full brief in concept_slides.md appendix and in this slide's notes.
Notes: Brief B-2 (Urbis / Arcadia): 1:5,000 at A3. Shortest public pedestrian route from the site's nearest pedestrian entry point to the nearest Castle Hill Metro station entrance, measured along footpaths and crossings, with the distance annotated (pack states about 623 m). State both end points and the date measured. Show the 400 m and 800 m walking catchments and the bus stop on Old Northern Road (routes 600, 603, 610X). Indicative only — not for determination.

## Slide 4: Current State policy asks for housing capacity that will actually be built, in serviced centres
STRATEGIC FRAMEWORK
FACT
The Sydney Plan (V1.0) commenced on 13 August 2026 with the State Land Use Plan as the current framework.
Source: R-e1 (to verify)
FACT
The SLUP Feasible Housing Capacity Policy (Appendix C) separates zoned capacity from capacity that is feasible and realisable.
Source: R-e2 (to verify)
FACT
The Hills Shire's target is 23,300 completed homes by 2029.
Source: R-g1 (to verify)
DESIGN PROPOSITION
YANA turns a 16 m control on a 2,048 m² lot into a defined, serviced, programmed scheme of 243 homes. The framework does not set its height or FSR.
Notes: Drafting note: Hard rule 2: no reliance on the Appendix D map, no radius claim, s9.1 direction not presented as binding on the EOI. Indicative only — not for determination.

## Slide 5: Castle Hill already has towers of 25 to 40 storeys in the State pipeline
COMPARATOR BOARD
Site | Storeys | Homes | Affordable offer | Status | Source
16-20 Old Castle Hill Rd | 40 | 371 | 42 homes, 15 years | Declared; EIS exhibited Oct 2026 | R-c1
2-4 & 22-28 Garthowen Cres | up to 36 | 355 | 15% of GFA | HDA briefing | Pack p17
36 Carrington Rd | up to 40 | 394 | 15% | Preparing EIS | Pack p16
325-329 Old Northern Rd | 25 | 148 | 5%, in perpetuity | SSD proposed | R-c5
YANA, 77-79 Cecil & 25 Hume | 38 + plant | 243 | 3%, in perpetuity | EOI | Pack p24
FACT
All comparator figures are from search-located records, to be verified against DPHI sources before lodgement.
Source: CA-0
DRAWING PLACEHOLDER
Brief B-5: Comparator board — centre massing
To: Furtado Sullivan / Arcadia
Full brief in concept_slides.md appendix and in this slide's notes.
Notes: Brief B-5 (Furtado Sullivan / Arcadia): One axonometric of the Castle Hill centre from the south-east, showing YANA and only schemes whose height is confirmed from a primary source at drafting: 16-20 Old Castle Hill Rd (40 storeys), 325-329 Old Northern Rd (25 storeys / 83.6 m), 2-4 & 22-28 Garthowen Cres (up to 36 storeys), 93-107 Cecil Ave (height per DPHI portal), Castle Hill Metro. Label each with storeys, status (declared / SSD lodged / proposed) and source. Do not show 'potential uplift' or TOD envelopes. Indicative only — not for determination.

## Slide 6: Current controls allow about 16 m; the proposal seeks 133.9 m through a concurrent rezoning
EXISTING CONTROL VS PROPOSAL
FACT
LEP height of buildings 16 m. No mapped FSR. Clause 4.1A minimum site area for a residential flat building is 4,000 m².
Source: Pack p14; locked position
FACT
The in-fill affordable housing bonus adds up to 30% height, to about 20.8 m.
Source: R-f2 (Urbis to verify)
DESIGN PROPOSITION
Proposal: 127.9 m to top of plant, 133.9 m including a 6 m design tolerance. Ground RL 121.00, top RL 254.90.
Source: Pack p24
MATTER FOR FUTURE
ASSESSMENT
Whether this height is appropriate is a matter for full merit assessment.
DRAWING PLACEHOLDER
Brief B-3: Existing-control line vs proposal elevation
To: Furtado Sullivan
Full brief in concept_slides.md appendix and in this slide's notes.
Notes: Brief B-3 (Furtado Sullivan): Two street elevations (Cecil Ave and Hume Ave) at 1:1,000, same scale, side by side. Draw: the 16 m LEP height plane; the in-fill affordable housing bonus plane at about 20.8 m (Urbis to confirm); the proposal to top of plant (RL 248.90, 127.9 m) and to the 6 m design-tolerance envelope (RL 254.90, 133.9 m). Label RLs, storeys and ground RL 121.00. No rendering; line drawing with a single tone for the proposal. Indicative only — not for determination.

## Slide 7: One slender tower on a two-level podium keeps the street active and the plate efficient
TOWER AND PODIUM FORM
DESIGN PROPOSITION
Ground floor: retail and residential lobby, 5.0 m floor-to-floor. Level 1: resident amenity, 4.5 m.
Source: Pack p24
DESIGN PROPOSITION
Typical tower floor (L4-L37): 945 m² gross building area, 735 m² GFA, 3.2 m floor-to-floor.
Source: Pack p24
DESIGN PROPOSITION
Outdoor communal open space about 30% of site area, with landscape and deep soil at ground level.
Source: Pack p27
MATTER FOR FUTURE
ASSESSMENT
Wind, overshadowing, ADG compliance and design quality are to be tested with the State Design Review Panel.
DRAWING PLACEHOLDER
Brief B-4: Tower and podium form
To: Furtado Sullivan
Full brief in concept_slides.md appendix and in this slide's notes.
Notes: Brief B-4 (Furtado Sullivan): Ground floor plan (retail, lobby, vehicle entry, deep soil, through-site movement if any), Level 1 amenity plan, typical tower plan (L4-L37: 945 m² GBA / 735 m² GFA, apartments per floor per the p24 floor types), and one section through podium and tower with floor-to-floor heights (GF 5.0 m, L1 4.5 m, typical 3.2 m) and basements (B1 4.5 m, B2 3.0 m). Show setbacks to Cecil and Hume Avenues and side boundaries, and the ADG separation achieved. Indicative only — not for determination.

## Slide 8: The neighbouring holdings keep developable footprints, subject to testing
ADJOINING-SITE DEVELOPABILITY
FACT
Draft site study shows indicative footprints on 81-87 Cecil Ave (8,416 m²) and a 2,600 m² adjoining lot to the south-west.
Source: Pack p23 (marked DRAFT; site red line to be corrected, B-0)
FACT
Existing built form is set back about 25 m (Cecil Ave) and 22 m (Hume Ave) from the site boundary.
Source: Pack p23
MATTER FOR FUTURE
ASSESSMENT
Separation, solar access and the south-west lot's own clause 4.1A position are to be demonstrated.
Source: Brief B-6
DRAWING PLACEHOLDER
Brief B-6: Adjoining-site developability study
To: Furtado Sullivan / Arcadia
Full brief in concept_slides.md appendix and in this slide's notes.
Notes: Brief B-6 (Furtado Sullivan / Arcadia): Plan and 3D massing showing a plausible residential envelope on each adjoining holding (81-87 Cecil Ave, 8,416 m²; the 2,600 m² adjoining lot to the south-west — not 25 Hume Ave, which is part of the site (owner, 5 Oct 2026); confirm its address), each meeting ADG building separation to YANA and achieving 2 hours mid-winter solar to 70% of its own apartments. State the assumed height and FSR for each and whether each meets cl 4.1A on its own. Include a mid-winter shadow overlay from YANA on both. Indicative only — not for determination.

## Slide 9: No fundamental servicing constraint has been found; built-form impacts are for the EIS
IMPACTS SUMMARY
FACT
Power, water, sewer and telecoms connections identified; one 150 mm sewer main at the north-east corner to divert or avoid.
Source: Pack p13
FACT
Heritage items nearby: Former Castle Hill Public School, St Paul's Cemetery and Wansbrough House.
Source: Pack p10
FACT
Flood, bushfire and contamination status not yet confirmed.
Source: s10.7 certificate outstanding (CA-3)
MATTER FOR FUTURE
ASSESSMENT
Overshadowing, wind, traffic, parking, heritage setting and views are to be assessed in the EIS.
Source: Brief B-7
DRAWING PLACEHOLDER
Brief B-7: Mid-winter shadow diagrams
To: Furtado Sullivan
Full brief in concept_slides.md appendix and in this slide's notes.
Notes: Brief B-7 (Furtado Sullivan): 21 June, hourly 9am-3pm, plan view, showing shadow from the 133.9 m envelope across adjoining residential land, Sherwin Avenue Reserve and the heritage items on pack p10 (Former Castle Hill Public School, St Paul's Cemetery, Wansbrough House). Note any public open space affected and for how long. Indicative only — not for determination.

## Slide 10: 243 homes across six apartment types, with 3% held as affordable housing in perpetuity
HOUSING AND AFFORDABLE HOUSING
17%
one-bed (42)
47%
two-bed (114)
26%
three-bed (63)
10%
four-bed (24)
FACT
Mix: 42 one-bed, 60 two-bed, 54 two-bed + study, 36 three-bed, 27 three-bed + study, 24 four-bed + study.
Source: Pack p24
DESIGN PROPOSITION
3% as affordable rental in perpetuity, secured in the LEP amendment: about 7 homes whether measured on GFA (about 866 m²) or on dwellings.
Source: Locked position; basis not yet decided (B-8)
MATTER FOR FUTURE
ASSESSMENT
Basis (GFA or dwellings), community housing provider, dwelling schedule and distribution are to be confirmed.
Source: Owner decision pending
DRAWING PLACEHOLDER
Brief B-8: Affordable housing schedule and distribution
To: Furtado Sullivan
Full brief in concept_slides.md appendix and in this slide's notes.
Notes: Brief B-8 (Furtado Sullivan): Schedule of affordable dwellings equal to 3% of residential GFA (about 866 m²; confirm count), by level and type, shown on a stacking diagram. Distribute across at least three levels; same finishes and amenity access as market apartments. Basis (GFA vs dwellings) not yet decided by the owner; show both counts. Indicative only — not for determination.

## Slide 11: SSD lodgement by October 2027, within 9 months of SEARs; construction by October 2029
DELIVERABILITY AND PROGRAMME
Oct 2026
EOI
22 Jan 2027
SEARs
1 Oct 2027
SSDA lodged
10 Oct 2028
Approval (programme)
by 10 Oct 2029
Construction start
FACT
Scoping and EIS preparation are programmed from 2 November 2026.
Source: Pack p26
FACT
Consolidated site; demolition is the only enabling work; no off-site infrastructure is needed first.
Source: Pack p3, p13
MATTER FOR FUTURE
ASSESSMENT
Target start date, builder and funding statement to be confirmed.
Source: Owner decision pending
Notes: Indicative only — not for determination.

## Slide 12: Only a concurrent rezoning can test this envelope; the in-fill bonus reaches about six storeys
WHY THIS PATHWAY
FACT
In-fill bonus: up to +30% height for 15% affordable for 15 years. On this site, about 20.8 m.
Source: R-f2 (Urbis to verify)
FACT
Clause 4.1A requires 4,000 m² for a residential flat building; the site is 2,048 m².
Source: Locked position
DESIGN PROPOSITION
The HDA pathway lets DPHI, council, agencies and the community assess the controls, design and public benefit together.
Source: Pack p6
MATTER FOR FUTURE
ASSESSMENT
Status of council's draft Castle Hill Precinct Plan to be confirmed at lodgement.
Source: R-f3; CA-4
Chart: Maximum height by pathway (m)
| LEP control | In-fill bonus | Proposal
Height | 16 | 20.8 | 133.9
Notes: Indicative only — not for determination.

## Slide 13
THE ASK
Declare YANA State significant development and issue SEARs so the envelope can be tested in full
DESIGN PROPOSITION
Amend The Hills LEP 2019 for the site: height of buildings, a site-specific clause 4.1A provision, and a provision securing 3% affordable housing in perpetuity.
MATTER FOR FUTURE
ASSESSMENT
Height, floor space, affordable housing and impacts to be tested through SEARs, design review, agency and council consultation and exhibition.
Notes: Indicative only — not for determination.